## Tracker
Page URL tested | Date In | Updated Page Content / Layout | Page / Section | Issues | Status | Type | Dev Notes/Resolution
GLOBAL CHANGES |  |  |  | Use original Innovive logo (on current website), Top Nav: Change "Services" to "Inno+ Vivarium Solutions", Remove "Talk to an Expert" , Add in "Order Products" (this will link to NetSuite - only those with a netsuite account can log in). PLEASE DO NOT put "trusted by" testimonials on every page. Only home page and Inno+ | Resolved
https://inno.myvoladolabs.com/ | 2026-06-03 |  | Homepage | Image: Choose different Image (work Victoria) to show more of our racks. the focus on this image is the changing station in background. Should be on racks in vivarium. Change the darker color to a dark navy, not black. | Open | Critical
|  |  |  | Remove the "Global precliical research" tag above the main header. Change main header to: "Research Ready from Day One" Subhead: Your leader in technology solutions and services for the modern vivarium". | Resolved |  | "Explore Solutions" can take you to the products page. What do you think?
|  |  |  | More homepage feedback: One Partner. header below the Hero should be changed to: One Partner for Your Pre-Clinical Research Needs: Paragraph below that - "Innovive helps research teams move faster with wash-free IVC products, expert vivarium services, and the industry’s only closed-loop recycling program". FOR THE THREE SECTIONS UNDER THAT: Where did the images go? Please add them back in. | Resolved
|  |  |  | Where did the Globe graphic go? Who is making these changes? Please add graphic back in. Change copy: Our commitment to excellence in research expands globally. | Resolved
|  |  |  | UPDATE FEEDBACK ON HOMEPAGE: 1. Change photo back to the one with multiple racks in vivarium but with new treatment (darken blue towards left side of image where headers are). 2. Fix navigation as discussed in today's call. 3. Get rid of tag "what we do". 4. Fix Globe image (it should really be a fade in background of this section not a squared off image) 5. Add in testimonials from current site 6. Where news releases are (add in some blog articles too). | Open | Critical | 6/11: Navigation rebuilt per call — top nav: Products (Mouse/Rat/Mouse&Rat dropdowns, Gnotobiotics under Mouse), The Innovive System (Research Ready lives here), Inno+ Vivarium Solutions, Company, Customer Portal (NetSuite). Contact = single CTA button. Homepage: section tags removed. GLOBE DONE — replaced the squared-off image with a new graphic: earth-horizon with international network arcs, applied as a true section background that fades into the page (per your feedback). Still in progress: homepage hero photo (awaiting your image pick w/ Victoria), testimonials (awaiting logos/quotes), news/blog content. RG Comment re Globe Graphic: Earlier today, this globe looked great, it was a faded image with international network arcs. Something changed, please fix back. The current one is not a true section background with fade.
https://inno.myvoladolabs.com/team/ | 2026-06-03 |  | Team | This page header show read: Innovive's Leadership Meet the team driving innovation and supporting research worldwide | Resolved
https://inno.myvoladolabs.com/gnotobiotics/ | 2026-06-03 |  | Gnotobiotics | Key Benefts section needs to include image of MVX3 lid. Change header: Gnotobiotics and the Innovive IVC System. Victoria Zimmerman What else can we say here? This sounds very generic and a bit outdated: "As microbiome research grows, maintaining gnotobiotic rodents in a germ-free setting is crucial. Traditionally, isolators have been the standard, but emerging studies support the use of IVC caging, especially disposable IVC caging, for effective germ-free maintenance". QUESTION: ARE WE PLACING THE "Trusted by..." and quotes on each page? I think it should only be on home page and on Inno+ pages if we don't have multiple quotes This is another example of a secondary page. It shoudl have a distinc look (the hero design treatment looks identical to home page) | In review | Polish
Suggest using image of a cage with MVX3 lid above the fold.
https://inno.myvoladolabs.com/products/enrichment/ | 2026-06-03 |  | Enrichment | Page not found | Resolved | Critical | Mouse and rat enrichment is combined to one link named "Enrichment". Please follow the updated link in A14.
https://inno.myvoladolabs.com/m-climb/ | 2026-06-03 |  | Mouse | How will user navigate from this page? Victoria ZimmermanI thought we were combining enrichment onto one page? Suggest adding crumbs to indicate location on website and system Mouse or Rat. | In review | Question
https://inno.myvoladolabs.com/m-divider2/ | 2026-06-03 |  | Mouse | How will user navigate from this page? Suggest adding crumbs to indicate location on website and system Mouse or Rat. | In review | Question
https://inno.myvoladolabs.com/innodome-innowheel/ | 2026-06-03 |  | Mouse | "How will user navigate from this page? Suggest adding crumbs to indicate location on website and system Mouse or Rat." | In review | Question
https://inno.myvoladolabs.com/innotube/ | 2026-06-03 |  | Mouse | How will user navigate from this page? Suggest adding crumbs to indicate location on website and system Mouse or Rat. | In review | Question
https://inno.myvoladolabs.com/m-innorichment/ | 2026-06-03 |  | Mouse | How will user navigate from this page? Suggest adding crumbs to indicate location on website and system Mouse or Rat. | In review | Question
https://inno.myvoladolabs.com/products/enrichment/crd-hld-h-3/ | 2026-06-03 |  |  | How will user navigate from this page? Suggest adding crumbs to indicate location on website and system Mouse or Rat. | Resolved | Question
https://inno.myvoladolabs.com/rat-feeders/ | 2026-06-03 | https://docs.google.com/document/d/1EkvmTs_gp1Dm12e0u8mZ_zFHgTnygBAdP0WhgbsC4ks/edit?usp=sharing | Rat | Information, tall rat wirebar are missing. See the provided google doc | Resolved | Critical | R-WIRE-TD can be found under "Tall" tab.
https://inno.myvoladolabs.com/r-innorichment/ | 2026-06-03 |  | Rat | How will user navigate from this page? | In review | Question
https://inno.myvoladolabs.com/r-loft-t/ | 2026-06-03 |  | Rat | How will user navigate from this page? Suggest adding crumbs to indicate location on website and system Mouse or Rat. | In review | Question
https://inno.myvoladolabs.com/rat-lid/ | 2026-06-04 | https://docs.google.com/document/d/1vae5Bcoh2ZSLM63TLlPnGB-32LzEG139DRzKHkJuuKM/edit?usp=sharing | Rat | Information, comparison table are missing. See the provided google doc | Resolved | Critical | Comparison table can be found in the attached link.
https://inno.myvoladolabs.com/inno/ | 2026-06-04 |  | Inno+ | This looks like an AI generated page. Please use the copy from the existing Inno+ page on our current website. Please spell "customised" as english version "customized" What are the tags on the photo? This page needs a lot of work. Things are oddly positioned. We also need a secondary page (need 2 Inno+ pages) per previous discussion. The proof points doing work here (that's for product). Need to emphasize flexibility, scalability of staffing and expert animal care 365 days a year. Let's discuss. I would rather use the current page with some modification (but moved to Wordpress) if this is too hard to figure out. | Resolved |  | Content copied exactly from the wix site. Design updated according to the given feedback.
https://inno.myvoladolabs.com/tall-rat-01/ | 2026-06-04 | https://docs.google.com/document/d/1mxV3mzm05w9KmFZvythpBvHCyVij0Pt6sAzgdUQejBA/edit?usp=sharing | Rat | See notes here. Compatible caging section should include Tall Rat Caging image and description from this page: https://www.innovive.com/rat-caging. The "view caging" link should point to https://www.innovive.com/tall-rat-caging-btm | Resolved | Minor
https://inno.myvoladolabs.com/mouse-lid/ | 2026-06-08 | https://docs.google.com/document/d/1P6yXrRiUOyPqsL99JCo0tKYbxTyvoX3_IjcwYyxsl0Y/edit?usp=sharing | Mouse | See google doc for comparion table and copy https://app.screencast.com/b1yOPK0qjyVy6 URL should be /mouse-lids MVX12 isn't lauched yet. Robin Gaffney Ok to keep w/ "Coming soon" in the table? Keep tab listing too? | Resolved | Critical | Table updated with the updated content in the doc. URL is: https://inno.myvoladolabs.com/mouse-lids/
https://inno.myvoladolabs.com/mouse-rack/# | 2026-06-08 | https://docs.google.com/document/d/1O06TD-GwpBPFafXKGNZSp4x9_HM3yaPYJ0zykEpPmXM/edit?usp=sharing | Mouse | URL should be /innorack-mouse https://app.screencast.com/MvqLQ2veMmJ0q | Resolved | Minor | Updated Link: https://inno.myvoladolabs.com/innorack-mouse/
https://inno.myvoladolabs.com/aquavive-mouse-water/ | 2026-06-08 |  | Mouse | Header language is missing. See https://www.innovive.com/aquavive-mouse-water Required cage components need to be mouse, not rat. Bottom should be first, then lid, feeder, water. | Resolved | Minor | Header language updated. Cage components updated as well.
https://inno.myvoladolabs.com/aquavive-rat-water/ | 2026-06-08 |  | Rat | Header language is missing. See https://www.innovive.com/aquavive-rat-water Required cage components need to be mouse, not rat. Bottom should be first, then lid, feeder, water. Remove "More Components Like this" Needs to be "Required Cage Components" | Resolved | Minor | Header language updated. Cage components updated as well.
https://inno.myvoladolabs.com/innorack-mouse/ | 2026-06-10 |  | Mouse | Layout is broken https://app.screencast.com/YyUkDlfm4WHmJ | Resolved | Critical | It might be the cache issue at that time. Seems fine now.
https://inno.myvoladolabs.com/products/ | 2026-06-10 |  | Products Category | Not sure this page is necesary. Visitors should enter Mouse and Rat Products from main navigarion. Robin Gaffney ? 6/16 This page is not necessary | In review | Minor
https://inno.myvoladolabs.com/about/ | 2026-06-11 |  | About Us |  | In review
https://inno.myvoladolabs.com/contact/ | 2026-06-11 |  | Contact Us |  | In review
https://inno.myvoladolabs.com/research-ready/ | 2026-06-11 |  | Research Ready | https://app.screencast.com/XfwDcD0TJPjqD Use "Research-Ready" on all references. Use this image for "Irradiated" section use this image for the double-bagged section | Resolved | Minor | You might have to hard-refresh. It might fix. Page seems fine even in incognito mode.
https://inno.myvoladolabs.com/privacy-policy/ | 2026-06-11 |  | Privacy Policy |  | In review
https://inno.myvoladolabs.com/terms-and-conditions/ | 2026-06-11 |  | Terms |  | In review
https://inno.myvoladolabs.com/ca-supply-chain/ | 2026-06-11 |  | Legal |  | In review
https://inno.myvoladolabs.com/mouse-feeders/ | 2026-06-11 |  | Mouse | https://app.screencast.com/KJxWTfapFMoIc Image needs to be seamless with the background https://app.screencast.com/Whyd4GnUN3CSv Adjust the space Required cage components should be mouse. Adjust acorss the site. Rat should reflect rat cage components, and mouse should be mouse. | Resolved | Minor | Fixed. Components now have the relevant products. Image border removed.
https://inno.myvoladolabs.com/tall-rat-xl/ | 2026-06-11 |  | Rat | Innorack Tall IVC Rat XL Features section font is off. https://app.screencast.com/5wkIMgqHW9Dz8 - adjust https://app.screencast.com/s4yB0OSnSG4xm | Resolved | Minor | Fixed. Table row style fixed and tax updated as well.
https://inno.myvoladolabs.com/rat-caging/ | 2026-06-11 |  | Rat | Visually inconsistent with other pages https://app.screencast.com/2JF6D31xydZHU 06/16 1. Rat Caging tab: add button to point to https://www.innovive.com/rat-caging-btm 2. Tall Rat Caging tab: add button to point to https://www.innovive.com/tall-rat-caging-btm 3. Tall Rat XL Caging: add button to point to: https://www.innovive.com/tall-xl-rat-caging-btm Match the details for each caiging configuration to this table: https://app.screencast.com/vo4g0N2NSmOzf. Keep featuers for all three from the original pages. | Open | Critical | Fixed. Removed all the unnecessary white-space.
https://inno.myvoladolabs.com/document-lookup/ | 2026-06-11 |  | Resources |  | In review
https://inno.myvoladolabs.com/how-it-works/ | 2026-06-12 |  | Innovive System | Visually inconsistent with other pages 06/16 https://app.screencast.com/bx8Iqn6CZYTtZ | Resolved | Critical | Page is updated now
https://inno.myvoladolabs.com/faq/ | 2026-06-12 |  | Resources | Questions are cut off https://app.screencast.com/1WOmoHYnRprOt 06/15 Too many varying colors: https://app.screencast.com/oq317Uhvh4uY5 | Resolved | Minor | Page is updated now
https://inno.myvoladolabs.com/patents/ | 2026-06-12 |  | Resources |  | In review
https://inno.myvoladolabs.com/events/ | 2026-06-12 |  | Resources | Too many varying colors, suggest using two: https://app.screencast.com/QEszwTNtHb9cr | Resolved | Minor | Page is updated now
https://inno.myvoladolabs.com/case-studies/ | 2026-06-12 |  | Resources |  | In review
https://inno.myvoladolabs.com/job-application/ | 2026-06-12 |  | Careers |  | In review
https://inno.myvoladolabs.com/profile-detail/ | 2026-06-12 |  | Team |  | In review
https://inno.myvoladolabs.com/sustainability/ | 2026-06-12 |  | About Us |  | In review | Critical
https://inno.myvoladolabs.com/innovive-water-process/ | 2026-06-12 |  | Innovive System | Suggest keeping this page unpublsihed when go live. The content is in progress | Resolved |  | For now, the page status in WP is "Pending Review"
https://inno.myvoladolabs.com/system-benefits/ | 2026-06-12 |  | Innovive System |  | Resolved
https://inno.myvoladolabs.com/recycling-eu/ | 2026-06-12 |  | Services |  | Resolved
https://inno.myvoladolabs.com/mouse-caging-m-btm-xl/ | 2026-06-12 |  | Mouse | 6/16 Include requierd caging component section: Mouse Xl bottom, RVX62 lid (rat lid), R-FEED-U + R-WBP, M-WB-850 (w/blue cap) Center the table | Resolved | Critical | Table is now horizontally centered. Added Caging components section at the bottom
https://inno.myvoladolabs.com/mouse-transportation-cart/ | 2026-06-12 |  | Mouse | 6/16 How will cust navigate from this page? Suggest adding Mouse IVC Caging and Innorack IVC Mouse sections under specs | Resolved | Critical | Added the section at the bottom to navigate to those pages.
https://inno.myvoladolabs.com/mouse-rat-bedding/ | 2026-06-12 |  | Mouse & Rat | remove borders around images: https://app.screencast.com/yPAXt80jjgHR6 6/16 Suggest adding Mouse IVC Systeam and Rat IVC System sections under the table | Resolved | Critical | Image border removed. Added the section at the bottom
https://inno.myvoladolabs.com/rat-racks/ | 2026-06-12 |  | Rat | 6/16 LInk each tab to individual page | Open | Minor
https://inno.myvoladolabs.com/innorack-rat/ | 2026-06-12 |  | Rat | 6/16 Use Rat Rack image: https://www.innovive.com/innorack-rat (currently Mouse rack shown) | Resolved | Critical | Replaced the image
https://inno.myvoladolabs.com/metabolic-cage-kit/ | 2026-06-12 |  | Mouse | 06/15 - remove this section: https://app.screencast.com/GZxhAsFLUsLj0 | Resolved | Minor | Removed the bottom section

## Dashboard
STATUS OVERVIEW
Status | Count | % of Total | Critical | Minor | Polish
Open | 4 | 8.333% | 3
In progress | 0 | 0% | 0
In review | 20 | 41.67% | 1
Resolved | 2 | 4.167% | 10
Deferred | 2 | 4.167% | 0
TOTAL | 48